## Gantt
Phase | Description | Start Date | End Date | Assigned | Status | 10/21 | 10/22 | 10/23 | 10/24 | 10/25 | 10/26 | 10/27 | 10/28 | 10/29 | 10/30 | 10/31 | 11/01 | 11/02 | 11/03 | 11/04 | 11/05 | 11/06 | 11/07 | 11/08 | 11/09 | 11/10 | 11/11 | 11/12 | 11/13 | 11/14 | 11/15 | 11/16 | 11/17 | 11/18 | 11/19 | 11/20 | 11/21 | 11/22 | 11/23 | 11/24 | 11/25 | 11/26 | 11/27 | 11/28 | 11/29 | 11/30 | 12/01 | 12/02 | 12/03 | 12/04 | 12/05 | 12/06 | 12/07 | 12/08 | 12/09 | 12/10 | 12/11 | 12/12 | 12/13 | 12/14 | 12/15 | 12/16 | 12/17 | 12/18 | 12/19 | 12/20 | 12/21
Requirements Analysis | Collect requirements, use cases | 2025-10-21 | 2025-10-26 | Hashem + Team | ✅Completed
System Design | ERD, DFD, DB design, Wireframes | 2025-10-26 | 2025-11-06 | Hashem + Assem + Heba + Ikhlas | ✅Completed
Environment Setup | DB + Backend + Frontend setup | 2025-11-07 | 2025-11-16 | Assem + Ikhlas + Heba | In Progress
Initial Development | UI + Login + Mood + Suggestions | 2025-11-16 | 2025-11-23 | Heba + Ikhlas | Not Started
Recommendation Integration | Improve logic + connect UI & API | 2025-11-23 | 2025-11-30 | Hashem + Ikhlas + Heba | Not Started
Testing & Fixes | Test and debug | 2025-11-30 | 2025-12-07 | Team | Not Started
Documentation | Report + Screenshots + diagrams | 2025-12-07 | 2025-12-14 | Hashem + Assem | Not Started
Final Presentation Prep | Slides + Demo + Poster | 2025-12-14 | 2025-12-21 | Team | Not Started